# TalentAI

# Implementation Plan

Agile Scrum delivery plan for the TalentAI AI-Powered Recruitment Application. Companion to the BRD/FRD, Requirements Specification, Business Rules & Acceptance Criteria, NFR Addendum, and Business Domains & Business State Model.

Version 1.0

Prepared by: Business Analysis Team

Date: August 29, 2026

Status: Draft — For Stakeholder Review

# 1. Executive Summary

TalentAI will be delivered using an Agile Scrum approach across five releases and twelve two-week delivery sprints (plus a Sprint 0 inception), spanning approximately seven months from kickoff to production go-live, followed by a four-week hypercare period. Delivery is sequenced by business value and technical dependency: platform foundation and core recruitment workflow first (Release 1), AI-differentiated capability once the data model is stable (Release 2), interview and offer workflow to complete the hire (Release 3), analytics (Release 4), and advanced integrations plus hardening (Release 5). This sequencing follows the rationale already established in BRD §5: "Everything else depends on identity, authorization, and ownership of recruitment data," and AI capability is introduced "once core recruitment data and workflow are stable."

Success is measured against the Business Objectives (BO-01–BO-08) and KPI targets defined in BRD §2.2 and §12, including a 30% reduction in time-to-hire, a 50% reduction in recruiter screening time, and zero material adverse findings in bias/fairness audits.

# 2. Implementation Strategy

- Phased, incremental delivery aligned to the BRD’s 9-phase roadmap (§5), sequenced by business value and technical dependency.

- Build core ATS functionality first (non-AI) to de-risk the program, then layer AI capability once the candidate/job data model is stable.

- Configuration-over-customization: workflow engine and scoring criteria configurable per organization, not hard-coded (Constraint C11).

- Human-in-the-loop by design: every AI-related sprint’s Definition of Done includes an explainability and override-path check (Constraint C01, C04).

- Pilot-first rollout: full lifecycle validated by at least 3 pilot hiring teams before general availability (per BRD §14 UAT approach).

# 3. Implementation Approach (Agile Scrum)

Delivery uses the Scrum framework with 2-week sprints and a single cross-functional squad (Section 12). Standard ceremonies apply: Sprint Planning, Daily Standup, Backlog Refinement, Sprint Review/Demo, and Retrospective. The backlog is structured using the traceability model already defined in BRD §5.12 (Business Requirement → Functional Requirement → Business Rule → User Story → Acceptance Criteria → Test Case), so every sprint’s committed stories trace directly back to an approved FR and its Given/When/Then acceptance criteria in the Business Rules & Acceptance Criteria document.

Definition of Ready: story has a linked FR/BR, Given/When/Then AC, and UX design (where applicable). Definition of Done: code merged, unit + SIT tests pass, AC demonstrated, accessibility checked (candidate-facing), and — for AI stories — explainability output verified.

# 4. Project Phases

| Project Phase | Maps to BRD Phase(s) | Approx. Duration |
| --- | --- | --- |
| Inception | Pre-Phase 1 discovery | 2 weeks |
| Release 1 — Foundation & Recruitment Core | Phases 1–3 | 8 weeks |
| Release 2 — AI Core | Phases 4–5 | 4 weeks |
| Release 3 — Interview & Hiring | Phases 6–7 | 6 weeks |
| Release 4 — Analytics & Insights | Phase 8 | 2 weeks |
| Release 5 — Advanced Integration & Hardening | Phase 9 (subset) | 4 weeks |
| Go-Live & Hypercare | n/a | 4 weeks |

# 5. Release Roadmap (Release 1–5)

| Release | Scope | Priority | Sprints | Key Outcome |
| --- | --- | --- | --- | --- |
| Release 1 — Foundation & Recruitment Core | BRD Phases 1–3 | P0 | Sprints 0–4 | Recruiters can create, approve, and publish jobs; candidates can register and apply — no AI yet |
| Release 2 — AI Core | BRD Phases 4–5 | P0 / P1 | Sprints 5–6 | AI resume parsing, explainable candidate matching, and structured screening operational |
| Release 3 — Interview & Hiring | BRD Phases 6–7 | P1 | Sprints 7–9 | End-to-end hire achievable: interview scheduling, evaluation, offer, and acceptance |
| Release 4 — Analytics & Insights | BRD Phase 8 | P2 | Sprint 10 | Recruitment dashboards and funnel/KPI reporting adopted by pilot TA leads |
| Release 5 — Advanced Integration & Hardening | BRD Phase 9 (subset) + BGV/Onboarding | P2 / P3 | Sprints 11–12 | Background verification, onboarding tracking (scope pending confirmation), priority integrations, security & performance hardening |

# 6–9. Sprint-Wise Implementation Plan

Sections 6 (sprint plan), 7 (features per sprint), 8 (sprint goals), and 9 (deliverables per sprint) are consolidated into a single table below for traceability — each row gives the sprint’s goal, the requirement references it delivers, and its exit deliverables.

| Sprint | Release | Sprint Goal | Key Features / Requirement Refs | Deliverables |
| --- | --- | --- | --- | --- |
| Sprint 0 | Inception | Establish delivery foundation: environment, backlog, architecture, vendor selection | AI/LLM vendor selection (D05); SSO/IdP discovery (D01); backlog grooming vs. BRD §7 | Approved sprint backlog; solution architecture doc; provisioned Dev/QA environments |
| Sprint 1 | R1 | Deliver secure login and role-based access foundation | US-001–005; FR-ADM-01/02; NFR-SEC-01/03/05 | Working SSO login; RBAC engine; audit log v1 |
| Sprint 2 | R1 | Enable recruiters to create and approve requisitions | US-006–011; FR-REQ-01–04 | Requisition create/edit/approve workflow |
| Sprint 3 | R1 | Enable job publishing and candidate-facing job search | US-012–014; FR-REQ-05–07; FR-JOB-01/08 | Job publish/close; source tracking; requisition search |
| Sprint 4 | R1 | Enable candidates to register, build a profile, and apply | US-015–022; FR-APP-01–09; NFR-USE-01 | Candidate portal MVP; resume upload; application creation & status |
| Sprint 5 | R2 | Deliver AI resume parsing with recruiter review/correction | US-023–025; BR-020–024; NFR-PERF-02 | AI resume parser in production; extracted-profile review UI |
| Sprint 6 | R2 | Deliver explainable AI matching and structured screening | US-026–038; FR-AI-01–05/08/10; NFR-AI-01–03 | Match score + explanation UI; screening engine; shortlisting pipeline |
| Sprint 7 | R3 | Enable end-to-end interview scheduling | US-039–044; FR-INT-01–04/07 | Calendar-integrated scheduling; invitations; reschedule/cancel |
| Sprint 8 | R3 | Enable structured interview evaluation and hiring decision | US-045–054; FR-INT-05/06/09; FR-OFF-01–03 | Scorecards; consolidated feedback; offer creation & approval workflow |
| Sprint 9 | R3 | Complete offer lifecycle and candidate-facing notifications | US-055–062; FR-OFF-04–07; FR-COM-01–04 | Offer accept/decline; e-signature integration; notification templates |
| Sprint 10 | R4 | Deliver recruitment dashboards and funnel analytics | US-063–066; FR-RPT-01–06 | Recruiter dashboard; time-to-fill/hire reporting; DEI funnel (consent-gated) |
| Sprint 11 | R5 | Deliver background verification and pre-boarding tracking | FR-BGV-01–04; FR-ONB-01–08 (scope pending — see note) | BGV vendor integration; onboarding checklist engine |
| Sprint 12 | R5 | Harden security/performance and complete priority integrations | FR-ADM-06; FR-AI-15/FR-RPT-05; NFR-SEC-02; NFR-SCAL-02 | Job-board integration; AI governance dashboard; performance & pen-test results |

Sprint 11 scope (Background Verification, Onboarding & Pre-boarding) is contingent on resolving the scope conflict identified in the Business Domains & Business State Model document: BRD §5.8 (Phase 7) lists "Employee onboarding" as out of scope, while §7.9 defines eight onboarding functional requirements. This should be confirmed with stakeholders no later than the Release 4 exit gate.

# 10. Entry Criteria and Exit Criteria per Release

| Release | Entry Criteria | Exit Criteria |
| --- | --- | --- |
| Release 1 | Approved backlog; environments ready; SSO/IdP credentials available (D01) | Recruiters can create/approve/publish jobs; candidates can register/apply; RBAC & audit logging verified in SIT |
| Release 2 | R1 signed off; AI/LLM service available (D05); model config framework ready (D06) | Match score + explanation displayed for 100% of parsed resumes in test set; human-in-the-loop control verified |
| Release 3 | R2 signed off; calendar & e-signature sandbox access confirmed | Full requisition-to-hire walkthrough completed by ≥1 pilot team; offer e-signature functional |
| Release 4 | R3 signed off; sufficient recruitment data present for reporting | Dashboards validated against defined KPI formulas (BR-052) |
| Release 5 | R4 signed off; vendor contracts finalized for chosen integrations | Pen-test critical findings resolved; priority integrations live in staging |

# 11. Milestones

| ID | Milestone | Target Date | Description |
| --- | --- | --- | --- |
| M1 | Kickoff | 14-Sep-2026 | Charter approved, team mobilized |
| M2 | Foundation Ready (R1 complete) | 20-Nov-2026 | Core ATS usable end-to-end without AI |
| M3 | AI Core Live (R2 complete) | 18-Dec-2026 | AI matching & screening operational |
| M4 | First End-to-End Hire (R3 complete) | 12-Feb-2027 | Pilot team completes a hire via TalentAI |
| M5 | Analytics Live (R4 complete) | 26-Feb-2027 | Recruitment dashboards adopted by pilot TA leads |
| M6 | Feature Freeze | 15-Mar-2027 | No new features; hardening only |
| M7 | UAT Sign-off | 02-Apr-2027 | 100% Must-Have FRs demonstrated; no open Sev1/Sev2 |
| M8 | Go-Live | 05-Apr-2027 | Production cutover |
| M9 | Hypercare Exit | 30-Apr-2027 | Support handed to BAU team |
| M10 | Post-Implementation Review | 30/60/90 days post go-live | KPI attainment vs. BO-01–08 reviewed |

# 12. Resource Plan

| Role | Allocation | Key Responsibilities | Primarily Engaged |
| --- | --- | --- | --- |
| Business Analyst | 1.0 FTE | Backlog grooming, traceability, acceptance criteria, UAT coordination | Throughout |
| Product Owner | 1.0 FTE | Prioritization, stakeholder sign-off, scope decisions | Throughout |
| Scrum Master | 1.0 FTE | Ceremonies, impediment removal, velocity tracking | Throughout |
| Solution Architect | 0.5 FTE | Technical design, integration architecture, NFR compliance | Sprint 0, R2, R5 |
| Backend Developers | 3.0 FTE | Core platform, workflow engine, integrations | Throughout |
| Frontend Developers | 2.0 FTE | Candidate portal, recruiter/HM UI | Throughout |
| AI/ML Engineer | 1.5 FTE | Resume parsing, matching engine, explainability, bias testing | R2 primarily, ongoing tuning |
| QA Engineers | 2.0 FTE | Test case design/execution, automation, UAT support | Throughout |
| UI/UX Designer | 1.0 FTE | Portal design, accessibility (WCAG AA), usability testing | R1, R3, ongoing |
| DevOps Engineer | 1.0 FTE | CI/CD, environments, scaling, monitoring | Throughout |
| Data Privacy / Compliance SME | 0.25 FTE | DPIA, consent design, bias-audit oversight | R2, R5, pre-go-live |
| Change Manager / Training Lead | 0.5 FTE | Adoption, training materials, champions network | R3 onward |

# 13. RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed. *Compliance is Consulted on requirements sign-off only where AI/privacy-related.

| Activity | BA | PO | SM | Arch | Dev/QA | Compl. | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements / AC sign-off | R | A | C | I | C | C* | I |
| Sprint planning & prioritization | C | A | R | I | C |  |  |
| Architecture & technical design | I | C | C | A/R | C |  |  |
| AI model governance / bias audit | C | I |  | C | R | A | I |
| Security & penetration test sign-off | I | C |  | R | C | C | A |
| UAT execution & sign-off | C | A | C | C | R | C | I |
| Go-live decision | C | R | I | C | C | C | A |
| Production support (hypercare) | I | I | I | C | R |  | I |

# 14. Work Breakdown Structure (WBS)

- 1.0 TalentAI Implementation

  - 1.1 Inception & Planning

    - 1.1.1 Charter & Governance

    - 1.1.2 Environment Setup

    - 1.1.3 Backlog Grooming

  - 1.2 Release 1 — Foundation & Recruitment Core

    - 1.2.1 User & Access Management

    - 1.2.2 Job / Requisition Management

    - 1.2.3 Candidate & Application Management

  - 1.3 Release 2 — AI Core

    - 1.3.1 AI Resume Parsing

    - 1.3.2 AI Candidate Matching & Explainability

    - 1.3.3 Screening & Shortlisting

  - 1.4 Release 3 — Interview & Hiring

    - 1.4.1 Interview Scheduling

    - 1.4.2 Interview Evaluation

    - 1.4.3 Hiring Decision & Offer Management

  - 1.5 Release 4 — Analytics

    - 1.5.1 Recruitment Dashboards

    - 1.5.2 KPI / Funnel Reporting

  - 1.6 Release 5 — Advanced Integration & Hardening

    - 1.6.1 Background Verification Integration

    - 1.6.2 Onboarding & Pre-boarding

    - 1.6.3 Security Hardening & Pen-Test Remediation

    - 1.6.4 Priority External Integrations

  - 1.7 Testing & Quality Assurance

    - 1.7.1 SIT

    - 1.7.2 UAT

    - 1.7.3 Performance & Security Testing

  - 1.8 Deployment & Cutover

  - 1.9 Hypercare & Post-Implementation Review

# 15. Dependency Matrix

| ID | Dependency | Impact | Required By |
| --- | --- | --- | --- |
| D01 | Authentication / Identity service | Required for user login and identity management | Release 1 |
| D02 | Role/permission mechanism | Required for RBAC and data access | Release 1 |
| D03 | Database | Required for users, jobs, candidates and applications | Release 1 |
| D04 | File/document storage | Required for resumes and offer documents | Release 1 |
| D05 | AI/LLM service | Required for resume parsing and AI matching | Release 2 |
| D06 | AI model/prompt configuration | Required for consistent AI extraction and matching | Release 2 |
| D07 | AI evaluation framework | Required to validate accuracy and quality of AI results | Release 2 |
| D08 | Email/notification service | Required for candidate and recruiter notifications | Release 1, 3 |
| D09 | Calendar integration | Required for automated interview scheduling | Release 3 |
| D10 | Document-generation capability | Required for automated offer generation | Release 3 |
| D11 | Organization master data | Required for departments, locations, job categories | Release 1 |
| D12 | Recruitment workflow definitions | Required to configure candidate lifecycle | Release 1 |
| D13 | Job requirement definitions | Required for meaningful candidate matching | Release 1 |
| D14 | Privacy/security policies | Required for handling candidate personal information | Release 1 |
| D15 | External platform APIs | Required for job-board/HRMS/calendar integrations | Release 5 |
| D16 | Reporting/analytics infrastructure | Required for recruitment dashboards | Release 4 |
| D17 | Cloud/infrastructure environment | Required to deploy and operate the application | Sprint 0 |

# 16. Risk Register with Mitigation

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | AI screening model exhibits adverse impact on protected groups | Medium | High | Quarterly bias audits; human-in-the-loop review | Compliance Officer |
| R-02 | Low candidate trust in AI ("black box") decisions | Medium | Medium | Explainable AI, transparent communication, opt-out/human review path | Product Owner |
| R-03 | Integration delays with legacy HRIS | High | Medium | Early technical discovery workshop; phased integration plan | Solution Architect |
| R-04 | Regulatory landscape for AI-in-hiring changes during build | Medium | High | Legal/Compliance review at each phase gate; configurable compliance controls | Compliance Officer |
| R-05 | Scope ambiguity on Onboarding & Background Verification (BRD §5.8 vs §7.9 conflict) | High | Medium | Resolve with stakeholders before Sprint 11 planning | Product Owner / BA |
| R-06 | AI/LLM vendor rate limits or cost overrun under load | Medium | Medium | Load testing in R2; configurable rate-limit handling | Solution Architect |
| R-07 | Delayed vendor contracts (job boards, background-check) | Medium | Medium | Engage procurement in Sprint 0 | Product Owner |
| R-08 | Key resource attrition (AI/ML Engineer, Architect) | Low | High | Knowledge documentation, pairing, backup SMEs | Scrum Master |
| R-09 | Candidate PII data residency requirements unresolved | Medium | High | Confirm operating regions and residency needs by end of R1 | BA / Compliance Officer |
| R-10 | UAT defects concentrated late in AI explainability/bias metrics | Medium | High | Continuous AI validation against held-out test set from Sprint 5 onward | QA Lead |

# 17. Communication Plan

| Audience | Channel | Frequency | Content Owner |
| --- | --- | --- | --- |
| Exec Sponsor / Steering Committee | Steering deck | Monthly | Product Owner |
| TA Leadership & Pilot Hiring Teams | Status email + sprint demo | Bi-weekly | BA / Scrum Master |
| Development Team | Standup, planning, review, retro | Daily / bi-weekly | Scrum Master |
| Compliance / Legal / Data Privacy Officer | Governance review | Each phase gate + monthly during R2/R5 | BA / Compliance SME |
| IT / Integration Partners | Technical sync | Bi-weekly during integration sprints | Solution Architect |
| Recruiters, Hiring Managers, Interviewers | Release notes + training sessions | Each release | Change Manager |
| Candidates (external) | In-app notice / FAQ update | Each candidate-facing release | Product Owner |

# 18. Change Management Plan

Change management follows a phased, pilot-first adoption model consistent with the BRD’s open question on phased/pilot rollout by business unit (§16):

- Stakeholder impact assessment by role (Recruiter, Hiring Manager, Interviewer, Candidate) completed before each release.

- Role-based training delivered per release, with dedicated material on interpreting AI match scores and explanations (critical given Constraint C04).

- A recruiter/hiring-manager champions network per business unit to provide peer support and feedback.

- Pilot rollout to at least 3 hiring teams before general availability, per the UAT approach in BRD §14.

- Office hours / feedback channel open during hypercare to capture adoption friction early.

# 19. Data Migration Strategy

Scope: open requisitions, active candidate pipeline data, and a defined window of historical closed requisitions/hires needed to establish the KPI baseline referenced in BO-01 and BO-02 ("reduce by 30% vs. baseline").

- Approach: phased extract-transform-load, sequenced with releases — organizational/user data migrated ahead of Release 1 go-live; requisition and candidate pipeline data migrated ahead of Release 1 general availability; closed/historical data migrated as read-only archive ahead of Release 4 (needed for baseline reporting).

- PII handling: migrated candidate data encrypted in transit/at rest (NFR-SEC-01); consent status re-validated for migrated candidate records per NFR-PRIV-04.

- Validation: reconciliation counts between source and target, plus recruiter spot-check of a sample of migrated candidate/requisition records before sign-off.

- Fallback: source system retained read-only for a defined retention window in case of migration defects.

# 20. Testing Strategy

| Test Level | Scope | Owner | Key Criteria |
| --- | --- | --- | --- |
| Unit Testing | Component-level logic, AI service mocks | Developers | ≥80% coverage on core services |
| SIT | Cross-module flows (requisition → application → AI match → interview → offer) | QA | All FR module integrations pass |
| UAT | Business scenario validation by pilot hiring teams | BA + Pilot Users | 100% Must-Have FRs demonstrated; zero open Sev1/Sev2 |
| Regression | Full automated suite before each release | QA (automated) | No previously-passed test regresses |
| Performance | Load test to 10,000 concurrent users; 3x seasonal spike | DevOps / QA | NFR-PERF-01, NFR-SCAL-02 targets met |
| Security / Penetration | Annual + pre-go-live pen test | External vendor | No unresolved critical findings |
| AI Fairness & Accuracy | Held-out test dataset, demographic parity check | AI/ML Engineer + Compliance | Documented accuracy/fairness metrics reviewed by Compliance |

# 21. Deployment Strategy

- Environment progression: Dev → SIT/QA → UAT/Staging → Production, with CI/CD pipeline and automated regression gate before promotion.

- Phased/pilot rollout by business unit ahead of full rollout, consistent with the change management approach in Section 18.

- Blue-green or canary production cutover to protect the 99.9% uptime target (NFR-AVAIL-01).

- Feature flags on AI capability so it can be disabled independently of a full rollback if an issue is isolated to AI processing (supports graceful degradation per Constraints C06/C07).

# 22. Rollback Plan

- Rollback triggers: Sev1 production defect, data integrity issue, or security incident.

- Target rollback completion within the 4-hour RTO defined in NFR-AVAIL-02.

- AI-specific issues addressed first via feature-flag disablement rather than a full release rollback, where isolated to AI processing.

- Database backup/restore procedure rehearsed in staging before go-live.

- Defined communication protocol to stakeholders during a rollback event, plus mandatory root-cause review before re-attempting deployment.

# 23. Hypercare & Production Support

A 4-week hypercare period follows go-live, staffed by a subset of the delivery team with elevated monitoring and daily defect triage. Severity-based SLAs apply: Sev1 same-day, Sev2 within 3 business days, Sev3 scheduled into the next release. Hypercare exit requires defect volume to stabilize, zero open Sev1/Sev2 items, and a signed-off support runbook handed to the BAU support team.

# 24. Success Metrics / KPIs

| KPI | Definition | Target |
| --- | --- | --- |
| Time-to-Fill | Days from requisition approval to offer acceptance | Reduce by 30% vs. baseline |
| Time-to-Hire | Days from candidate application to offer acceptance | Reduce by 30% vs. baseline |
| Recruiter Screening Time | Avg. hours spent manually screening per requisition | Reduce by 50% |
| AI Match Score Adoption | % of recruiters actively using AI ranking to shortlist | 80%+ within 6 months |
| AI Override Rate | % of AI top-ranked candidates NOT shortlisted by recruiter | Tracked; investigated if >40% |
| Candidate Satisfaction (CSAT) | Post-process candidate survey score | 4.2 / 5 or higher |
| Offer Acceptance Rate | % of extended offers accepted | 85%+ |
| Day-1 Readiness Rate | % of new hires with full access/equipment on start date | 90%+ |
| Cost-per-Hire | Total recruiting cost / number of hires | Reduce by 15% |

# 25. Project Timeline

Kickoff is targeted for 14-Sep-2026. Sprint 0 plus twelve 2-week delivery sprints (26 weeks, including a 2-week holiday buffer around year-end) leads to a go-live target of 05-Apr-2027 — approximately 7 months, within the BRD’s assumed 6–8 month implementation window. A 4-week hypercare period follows, with post-implementation reviews at 30, 60, and 90 days after go-live.

# 26. High-Level Gantt-Style Implementation Schedule

| Phase / Milestone | Start | End | Duration |
| --- | --- | --- | --- |
| Inception (Sprint 0) | 14-Sep-2026 | 25-Sep-2026 | 2 wks |
| Release 1 — Foundation & Recruitment Core (Sprints 1–4) | 28-Sep-2026 | 20-Nov-2026 | 8 wks |
| Release 2 — AI Core (Sprints 5–6) | 23-Nov-2026 | 18-Dec-2026 | 4 wks |
| Holiday Buffer | 21-Dec-2026 | 01-Jan-2027 | 2 wks |
| Release 3 — Interview & Hiring (Sprints 7–9) | 04-Jan-2027 | 12-Feb-2027 | 6 wks |
| Release 4 — Analytics & Insights (Sprint 10) | 15-Feb-2027 | 26-Feb-2027 | 2 wks |
| Release 5 — Advanced Integration & Hardening (Sprints 11–12) | 01-Mar-2027 | 26-Mar-2027 | 4 wks |
| UAT & Go-Live Readiness | 29-Mar-2027 | 02-Apr-2027 | 1 wk |
| Go-Live | 05-Apr-2027 | 05-Apr-2027 | Cutover |
| Hypercare | 05-Apr-2027 | 30-Apr-2027 | 4 wks |
| Post-Implementation Review | 30/60/90 days post go-live | — | — |

# 27. Assumptions, Constraints, Risks, and Dependencies

Full risk and dependency detail is maintained in Sections 15 and 16. Key assumptions and constraints carried forward from the BRD are summarized below.

## Assumptions

| ID | Statement |
| --- | --- |
| A1 | AI services (resume parsing, matching) will be available and reliable throughout delivery. |
| A2 | Email/notification service and calendar APIs (Outlook/Google) will be available and configured. |
| A3 | The organization has approved the recruitment workflow stages used to configure the pipeline. |
| A4 | Users will have internet access and modern browser support. |
| A5 | Candidate resumes will be supplied in PDF, DOC, or DOCX format. |
| A6 | Authorized recruiters/hiring managers will review AI recommendations before final decisions (BRD A9). |

## Constraints

| ID | Statement |
| --- | --- |
| C01 | The system shall not make the final recruitment decision solely on the basis of AI output. |
| C04 | AI-generated candidate recommendations must provide sufficient supporting information for recruiter review. |
| C09 | The system must operate within agreed performance SLAs for search, application processing, and AI processing. |
| C10 | Initial release concurrency/scale limits must be quantified during technical design (currently open). |
| C11 | Recruitment policy should be configurable, not hard-coded, where it varies by organization. |
| C12 | AI-based recruitment features must support compliance with employment, privacy, anti-discrimination, and AI governance requirements. |

# 28. Deliverables by Phase

| Phase / Release | Key Deliverables |
| --- | --- |
| Inception | Approved backlog; solution architecture document; provisioned environments |
| Release 1 | Working RBAC/SSO; requisition workflow; candidate application portal MVP |
| Release 2 | AI resume parser; explainable match scoring; screening/shortlisting engine |
| Release 3 | Interview scheduling & evaluation; offer generation & e-signature |
| Release 4 | Recruitment dashboards; KPI/funnel reporting |
| Release 5 | Background verification & onboarding tracking (scope pending); priority integrations; security/performance hardening |
| Go-Live & Hypercare | Production cutover; hypercare support; BAU handover |
| Post-Implementation | KPI attainment report; lessons-learned register; Phase 9 advanced-AI backlog |

# 29. Go-Live Checklist

- 100% of Must-Have (M) functional requirements demonstrated successfully in UAT.

- No open Severity 1 (Critical) or Severity 2 (High) defects at UAT sign-off.

- AI matching/screening validated against a held-out test dataset with documented accuracy and fairness metrics reviewed by Compliance.

- End-to-end lifecycle walkthrough (requisition → hire → onboarding) completed by at least 3 pilot hiring teams.

- Security and penetration test completed with no unresolved critical findings.

- Data Privacy Impact Assessment (DPIA) completed and signed off.

- Data migration reconciliation validated by recruiter spot-check.

- Rollback plan tested in staging.

- Hypercare support model and runbook approved.

- Executive Sponsor / Steering Committee go-live sign-off obtained.

# 30. Post-Implementation Review

Reviews are conducted at 30, 60, and 90 days after go-live, assessing KPI attainment against the Business Objectives (BO-01–BO-08, BRD §2.2) and KPI targets (BRD §12, reproduced in Section 24 above). The review captures lessons learned and formally hands off any deferred scope — including resolution of the Onboarding/Background Verification scope conflict if not closed pre-go-live, and the Phase 9 advanced-AI backlog (job-board integrations, AI-generated job descriptions/interview questions, conversational recruiter assistant) — into ongoing product roadmap governance.